# 06. Engagement Team Planning and Time-Table

## 1. Engagement Overview

Client Name: ABC Limited

Audit Period: 1st April 20X(Y-1) – 31st March 20XY

Engagement Partner: CA. Dharmaraj

EQCR: CA. Dronacharya

Industry: [Industry, e.g. Automobile]

Reporting Framework: Ind ASs notified under Companies (Ind AS) Rules 2015

Group Audit Engagement: [Yes / No]

## 2. Engagement Team Structure

| Role | Name | Responsibilities |
| --- | --- | --- |
| Engagement Partner | CA. Dharmaraj | Overall responsibility, final sign-off, liaison with TCWG |
| EQCR | CA. Dronacharya | Independent review of significant judgments, audit quality |
| Engagement Managers | CA. Bhim & CA. Arjun | Day-to-day supervision, timelines, managing client |
| Audit Supervisor | CA. Sahdev | Planning execution, supervising team, coordinating with client |
| Audit Staff | CA. Abhimanyu, CA. Ghatotkacha & [others] | Performing fieldwork, testing, documentation |
| IS Specialist | CA. Nakul | Review of ERP controls, ITGCs, automated controls |
| Tax Specialist | [Name] | Review of tax provisions, transfer pricing, deferred tax |
| Valuation/Actuarial Expert | [Name] | Employee benefits, impairment computation, fair value |

## 3. Location-wise Estimated Hours

| Location/Area | Current Year Est. (Hours) | Last Year Actual (Hours) |
| --- | --- | --- |
| SFS of ABC Limited |  |  |
| Corporate Office | [400] | [300] |
| [Manufacturing Plant 1] | [200] | [150] |
| [Manufacturing Plant 2] | [250] | [200] |
| Sales & Marketing Division | [300] | [250] |
| SFS Total | [1,200] | [1,000] |
| CFS of ABC Limited |  |  |
| Corporate Office | [500] | [500] |
| Other Auditors — Corporate Office | [400] | [300] |
| Other Auditors — On-site | [600] | [400] |
| CFS Total | [1,500] | [1,200] |

## 4. Key Planning Activities and Timeline

| Phase | Activity | Responsible | Target Date |
| --- | --- | --- | --- |
| Pre-Engagement | Acceptance, independence confirmation, engagement letter | Engagement Partner / Managers | [Date] |
| Planning | Business understanding, risk assessment, materiality | Partner / Managers / Supervisor | [Date] |
| Planning | Group Audit Instructions to Other Auditors | Managers | [Date] |
| Planning | Internal control walkthroughs, ITGC testing | Supervisor / IS Auditor | [Date] |
| Planning | ASM preparation and approval | Managers / Partner | [Date] |
| Planning | Communication with Audit Committee | Engagement Partner | [Date] |
| Interim Audit | Control testing, walkthroughs, interim substantive testing | Engagement Team | [Date] |
| Year-End Audit | Substantive testing of balances & disclosures | Engagement Team | [Date] |
| Year-End Audit | Expert involvement (Tax, Valuation, IS Audit) | Respective Expert | [Date] |
| Year-End Audit | Review of component auditors' work (Group Audit) | Partner / Managers | [Date] |
| Completion | Evaluation of misstatements, going concern, subsequent events | Partner / Managers | [Date] |
| Completion | EQCR completion | EQCR Reviewer / Partner | [Date] |
| Completion | Draft audit report discussion with Management | Engagement Partner | [Date] |
| Completion | Final report — Audit Committee / TCWG | Engagement Partner | [Date] |